Proposed Work Plan & Time-line:

Task 1. Research, Design, Planning and Organization of the Summit (Oct, Nov and Dec-2010)

- Tasks to be accomplished in Oct-2010

  - Set up Ontology Summit 2011 mailing lists (organizers; discussion)

  - Review suggestions collected from the community during the OntologySummit2010 follow-up (postmortem) session - ref. http://ontolog.cim3.net/cgi-bin/wiki.pl?ConferenceCall_2010_04_15

  - Call an online meeting of the core co-organizers: Ontolog, NIST, NCOR, NCBO, IAOA and possibly other core parties that may be involved in the next summit

  - Come up with a shortlist of candidate themes for OntologySummit2011

- Tasks to be accomplished in Nov-2010

  - Start discussing the candidate summit theme via the mailing list

  - Explore possibilities of engaging key communities for respective themes in the theme shortlist

  - Have a virtual panel session to help finalize on the choice of OntologySummit2011 theme

- Tasks to be accomplished in Dec-2010

  - Finalize the OntologySummit2011 theme

  - Identify the co-organizers of OntologySummit2011

  - Set up the OntologySummit2011 organizing committee

  - Write-up the OntologySummit2011 Title/Goal/Objective/Description statements

  - Start recruiting OntologySummit2011 Advisory Committee and OntologySummit2011 co-sponsors

  - Set up the event plan & schedule for OntologySummit2011 (spanning Jan~Mar/Apr-2011)

  - Lock-in the OntologySummit2011 Symposium Dates (event to be held at the NIST campus in Gaithersburg, MD)

Task 2. Summit Program Deployment (Jan-July, 2011)

- Convening a series of virtual activities that will span a period of about 3 months (Jan-March, 2011) that culminate in a 2-day symposium at NIST during which findings are reported, key issues discussed and deliberated, and the message (and report of findings and recommendations) documented in a Summit Communiqué. The process and activities typically involve the following elements:

  - Virtual discussion on the theme of the Summit, guided by volunteer champions along identified sub-theme or tracks, over a dedicated archived discussion list

  - Multiple virtual panel sessions, invited talks, open discussions in the form of augmented conference calls

  - Research studies, surveys, analysis, synthesis and reporting

  - Drafting of the Summit Communiqué (and the virtual discourse associated with that) so that a near-final draft can be presented for discussion at the Summit Symposium

  - Convening the Summit Symposium - a 2-day face-to-face event with remote participation support (March or April, 2011)

  - Post-processing of Summit resources and deliverables (May-July, 2011)

  - Virtual follow-up session to review the Summit activities, identify and spin-off projects and initiatives as appropriate, and do some pre-planning for the next Summit

Progress reports will be submitted to NIST as required.